## Migration Plan
# | Live URL (windchasers.in) | Type | Status | New App Route (target) | Role | Group | Internal Links | Notes
1 | /blog/ | Page | MIGRATE | /blog | Hub | Blog | all posts | Blog index
2 | /category/blog/ | Category | MIGRATE | /category/blog | Hub | Blog | all posts | Archive — or fold into /blog
3 | /best-aviation-academy-in-india-for-pilot-training-a-career-ready-curriculum/ | Post | MIGRATE | (same slug) | Leaf | Blog | /blog | Real post
4 | /how-to-start-your-helicopter-flight-training-a-step-by-step-guide/ | Post | MIGRATE | (same slug) | Leaf | Blog | /blog + /helicopter-training | Real post
5 | /a-complete-guide-to-dgca-ground-classes-in-india-subjects-duration-and-benefits/ | Post | MIGRATE | (same slug) | Leaf | Blog | /blog + /dgca-ground-classes | Real post
6 | /best-online-aviation-courses-in-india-flexible-learning-for-future-flyers/ | Post | MIGRATE | (same slug) | Leaf | Blog | /blog | Real post
7 | /about/ | Page | MIGRATE | /about | Core | Brand | /windchasers-meet-the-team + /with-the-founder | Pick ONE canonical (about vs about-us)
8 | /about-us/ | Page | MIGRATE | /about-us | Core | Brand | 301 → /about (or vice-versa) | Duplicate About — choose canonical
9 | /windchasers-meet-the-team/ | Page | MIGRATE | /windchasers-meet-the-team | Core | Brand | /about | App /team becomes alias/redirect
10 | /with-the-founder/ | Page | MIGRATE | /with-the-founder | Core | Brand | /about | Could fold into About
11 | /contact-us/ | Page | MIGRATE | /contact-us | Core | Brand | global (footer/nav) | Verified contact details
12 | /cabin-crew-program/ | Page | MIGRATE | /cabin-crew-program | Leaf | Cabin Crew | /cabin-crew (hub) | App /cabin-crew becomes hub
13 | /dgca-ground-classes/ | Page | MIGRATE | /dgca-ground-classes | Leaf | Ground | /dgca (hub) | App /dgca becomes hub
14 | /diploma-in-aviation/ | Page | MIGRATE | /diploma-in-aviation | Leaf | Ground | /dgca (hub) | Core SEO
15 | /ielts-training-program/ | Page | MIGRATE | /ielts-training-program | Leaf | Ground | /dgca (hub) | Core SEO
16 | /helicopter-training/ | Page | MIGRATE | /helicopter-training | Leaf | Helicopter | /helicopter (hub) | App /helicopter becomes hub
17 | /privacy-policy/ | Page | MIGRATE | /privacy-policy | Core | Legal | footer | Legal
18 | /refund-policy/ | Page | MIGRATE | /refund-policy | Core | Legal | footer | Legal
19 | /terms-conditions/ | Page | MIGRATE | /terms-conditions | Core | Legal | footer | Legal
20 | /commercial-pilot-license/ | Page | MIGRATE | /commercial-pilot-license | Leaf | Licenses | /pilot-training (hub) + sibling licenses | Core SEO
21 | /private-pilot-license/ | Page | MIGRATE | /private-pilot-license | Leaf | Licenses | /pilot-training (hub) | Core SEO
22 | /airline-transport-pilot-license/ | Page | MIGRATE | /airline-transport-pilot-license | Leaf | Licenses | /pilot-training (hub) | Core SEO
23 | /foreign-cpl/ | Page | MIGRATE | /foreign-cpl | Leaf | Licenses | /pilot-training (hub) + /license-conversion-course | Core SEO
24 | /license-conversion-course/ | Page | MIGRATE | /license-conversion-course | Leaf | Licenses | /pilot-training (hub) + /foreign-cpl | Core SEO
25 | /pilot-training-in-india/ | Page | MIGRATE | /pilot-training-in-india | Leaf | Locations | /international (hub) + 5 sibling countries | Geo SEO
26 | /pilot-training-in-usa/ | Page | MIGRATE | /pilot-training-in-usa | Leaf | Locations | /international (hub) + siblings | Geo SEO
27 | /pilot-training-in-canada/ | Page | MIGRATE | /pilot-training-in-canada | Leaf | Locations | /international (hub) + siblings | Geo SEO
28 | /pilot-training-in-australia/ | Page | MIGRATE | /pilot-training-in-australia | Leaf | Locations | /international (hub) + siblings | Geo SEO
29 | /pilot-training-in-new-zealand/ | Page | MIGRATE | /pilot-training-in-new-zealand | Leaf | Locations | /international (hub) + siblings | Geo SEO
30 | /pilot-training-in-south-africa/ | Page | MIGRATE | /pilot-training-in-south-africa | Leaf | Locations | /international (hub) + siblings | Geo SEO
31 | /women-in-aviation/ | Page | MIGRATE | /women-in-aviation | Standalone | Other | /about + /pilot-training | Core SEO
32 | /pre-cadet-program/ | Page | MIGRATE | /pre-cadet-program | Leaf | Programs | /airline (hub) + /cadet-pilot-program | Core SEO
33 | /cadet-pilot-program/ | Page | MIGRATE | /cadet-pilot-program | Leaf | Programs | /airline (hub) + /pre-cadet-program | Core SEO
34 | /airline-preparation-program/ | Page | MIGRATE | /airline-preparation-program | Leaf | Programs | /airline (hub) | Core SEO
35 | /airline-cadet-program-interview-training/ | Page | MIGRATE | /airline-cadet-program-interview-training | Leaf | Programs | /airline (hub) | Core SEO
36 | /airline/ | Page | MIGRATE | /airline | Hub | Programs | all program leaves | New hub for cadet/airline programs
37 | /instrument-rating/ | Page | MIGRATE | /instrument-rating | Leaf | Ratings | /pilot-training (hub) + sibling ratings | Core SEO
38 | /multi-engine-rating/ | Page | MIGRATE | /multi-engine-rating | Leaf | Ratings | /multi-engine-instrument-rating-meir | Core SEO
39 | /multi-engine-instrument-rating-meir/ | Page | MIGRATE | /multi-engine-instrument-rating-meir | Leaf | Ratings | /multi-engine-rating | Core SEO (drop dup post)
40 | /certified-flight-instructor/ | Page | MIGRATE | /certified-flight-instructor | Leaf | Ratings | /pilot-training (hub) | Core SEO
41 | /night-rating-progam/ | Page | MIGRATE | /night-rating-progam | Leaf | Ratings | /pilot-training (hub) | Keep live typo "progam"
42 | /boeing-737-type-rating/ | Page | MIGRATE | /boeing-737-type-rating | Leaf | Type Ratings | /type-rating (new hub) + A320 | Core SEO
43 | /airbus-a320-type-rating/ | Page | MIGRATE | /airbus-a320-type-rating | Leaf | Type Ratings | /type-rating (new hub) + B737 | Core SEO
44 | / | Page | HUB | / | Hub | Brand | everything | Home exists; merge live content if desired
45 | /airport-operations-webinar/ | Page | SKIP | /webinar | — | Funnel |  | App has it
46 | /airport-operations-webinar-parents/ | Page | SKIP | /webinar/parents | — | Funnel |  | App has it
47 | /open-house/ | Page | SKIP | /open-house | — | Funnel |  | App has it
48 | /nz-event-rsvp/ | Page | SKIP | /nz-seminar | — | Funnel |  | App has it
49 | /thank-you/ | Page | SKIP | /thank-you | — | Funnel |  | App has it
50 | /pilot-assessment-test/ | Page | SKIP | /assessment | — | Funnel |  | App has assessment
51 | /pilot-assesment-test/ | Page | SKIP | /assessment | — | Funnel |  | Typo dup
52 | /pat2/ | Page | SKIP | /assessment | — | Funnel |  | Assessment variant
53 | /pat3/ | Page | SKIP | /assessment | — | Funnel |  | Assessment variant
54 | /pat4-0/ | Page | SKIP | /assessment | — | Funnel |  | Assessment variant
55 | /pilot-assesment-student-onbaording/ | Page | SKIP | /assessment | — | Funnel |  | Onboarding
56 | /join-windchasers/ | Page | SKIP | — | — | Funnel |  | Recruitment landing
57 | /join-windchasers-proxe/ | Page | SKIP | — | — | Funnel |  | Recruitment landing
58 | /cabin-crew-launch/ | Page | SKIP | — | — | Funnel |  | Campaign landing
59 | /pilot-training-consultation/ | Page | SKIP | /demo | — | Funnel |  | Consultation funnel
60 | /scholarship-application-form/ | Page | SKIP | — | — | Funnel |  | Form
61 | /cpl-enquiry/ | Page | SKIP | — | — | Funnel |  | Form
62 | /e-registration/ | Page | SKIP | — | — | Funnel |  | Form
63 | /priority-pass/ | Page | SKIP | — | — | Funnel |  | Lead magnet
64 | /pilot-roadmap-guide-2025/ | Page | SKIP | — | — | Funnel |  | Lead magnet
65 | /dgca-demo-sessions/ | Page | SKIP | — | — | Funnel |  | Demo funnel
66 | /cabin-crew-purchase-confirm/ | Page | SKIP | — | — | Transactional |  | Confirm
67 | /cabincrew-thankyou/ | Page | SKIP | — | — | Transactional |  | Thank-you
68 | /about-thank-you/ | Page | SKIP | — | — | Transactional |  | Thank-you
69 | /pat-thank-you/ | Page | SKIP | — | — | Transactional |  | Thank-you
70 | /pilot-assesment-thank-you/ | Page | SKIP | — | — | Transactional |  | Thank-you
71 | /pilot-assessment-thank-you-2/ | Page | SKIP | — | — | Transactional |  | Thank-you
72 | /checkout/ | Page | SKIP | — | — | WooCommerce |  | Woo
73 | /cart/ | Page | SKIP | — | — | WooCommerce |  | Woo
74 | /my-account/ | Page | SKIP | — | — | WooCommerce |  | Woo
75 | /shop/ | Page | SKIP | — | — | WooCommerce |  | Woo
76 | /some/ | Page | DROP | 301 → /license-conversion-course | — | Junk |  | Draft dup
77 | /home2/ | Page | DROP | 301 → / | — | Junk |  | Dup homepage draft
78 | /windchasers-anybody-can-fly-top-pilot-training-academy/ | Page | DROP | 301 → / | — | Junk |  | Old home draft
79 | /privacy-policy-2/ | Page | DROP | 301 → /privacy-policy | — | Junk |  | Dup
80 | /aviation-safety-briefing/ | Post | DROP | 301 → /blog | — | Thin |  | Thin lead post
81 | /industry-partnership-announcement/ | Post | DROP | 301 → /blog | — | Thin |  | Thin lead post
82 | /pilot-career-workshop/ | Post | DROP | 301 → /blog | — | Thin |  | Thin lead post
83 | /advanced-flight-training-demo/ | Post | DROP | 301 → /blog | — | Thin |  | Thin lead post
84 | /multi-engine-instrument-rating-meir/ (post) | Post | DROP | 301 → /multi-engine-instrument-rating-meir | — | Thin |  | Dup of page

## Routing Map
Group | Hub (existing/new app route) | Leaf SEO pages (recreated at SAME live slugs)
Licenses | /pilot-training (existing → hub) | /commercial-pilot-license, /private-pilot-license, /airline-transport-pilot-license, /foreign-cpl, /license-conversion-course
Ratings | /pilot-training (existing → hub) | /instrument-rating, /multi-engine-rating, /multi-engine-instrument-rating-meir, /certified-flight-instructor, /night-rating-progam
Type Ratings | /type-rating (NEW hub) | /boeing-737-type-rating, /airbus-a320-type-rating
Ground & Academics | /dgca (existing → hub) | /dgca-ground-classes, /diploma-in-aviation, /ielts-training-program
Cadet & Airline Programs | /airline (NEW hub) | /pre-cadet-program, /cadet-pilot-program, /airline-preparation-program, /airline-cadet-program-interview-training
Locations | /international (existing → hub) | /pilot-training-in-india, -usa, -canada, -australia, -new-zealand, -south-africa
Helicopter | /helicopter (existing → hub) | /helicopter-training
Cabin Crew | /cabin-crew (existing → hub) | /cabin-crew-program
Brand | / (home) + /about | /about, /windchasers-meet-the-team, /with-the-founder, /contact-us, /women-in-aviation
Blog | /blog (hub) | 4 real posts (same slugs) + /category/blog
Legal | footer | /privacy-policy, /refund-policy, /terms-conditions

## Current App Pages
Route (new app) | Role | Notes
/ | HUB | Home (top of funnel, links to all hubs)
/pilot-training | HUB | Becomes Licenses + Ratings hub
/dgca | HUB | Becomes Ground/Academics hub (→ /dgca-ground-classes)
/helicopter | HUB | Becomes Helicopter hub (→ /helicopter-training)
/cabin-crew | HUB | Becomes Cabin Crew hub (→ /cabin-crew-program)
/international | HUB | Becomes Locations hub (→ 6 country pages)
/team | HUB | Alias/301 → /windchasers-meet-the-team
/open-house | SKIP | Live /open-house covered
/webinar | SKIP | Live webinar covered
/webinar/parents | SKIP | Covered
/webinar/students | SKIP | Variant
/assessment | SKIP | Live PAT covered
/assessment/early | SKIP | Variant
/nz-seminar | SKIP | Live /nz-event-rsvp covered
/thank-you | SKIP | Covered
/demo | SKIP | Live /pilot-training-consultation
/pilot-training-students | APPONLY | App campaign funnel
/pilot-training-parents | APPONLY | App campaign funnel
/flight-schools | APPONLY | App feature (map)
/summercamp | APPONLY | App campaign
/atc | APPONLY | App campaign
/agent | APPONLY | Internal tool
/gtm | APPONLY | Internal tool
/stitch | APPONLY | Internal tool
/admin | APPONLY | Internal tool

## Legend & Summary
WindChasers Migration — Routing model: keep every live slug as its own route; existing app pages become hubs.
Color legend
MIGRATE | MIGRATE — rebuild at the SAME live slug (own route)
HUB | HUB — existing app page kept as overview; SEO pages link into it
SKIP | SKIP — funnel/event/transactional/Woo (already covered / not needed)
DROP | DROP — junk/duplicate/thin → 301 redirect to nearest live page
APPONLY | APP-ONLY — exists in new app, not on live (keep as-is)
Counts
Status | Count
MIGRATE | 43
HUB | 1
SKIP | 31
DROP | 9
TOTAL | =SUM(B12:B15)