## Migration Plan
# | Live URL (windchasers.in) | Type | Category | Status | New-App Equivalent | Action / Notes
1 | /blog/ | Page | Blog | MIGRATE | — | Blog index
2 | /category/blog/ | Category | Blog | MIGRATE | — | Archive — or fold into /blog
3 | /best-aviation-academy-in-india-for-pilot-training-a-career-ready-curriculum/ | Post | Blog | MIGRATE | — | Real post
4 | /how-to-start-your-helicopter-flight-training-a-step-by-step-guide/ | Post | Blog | MIGRATE | — | Real post
5 | /a-complete-guide-to-dgca-ground-classes-in-india-subjects-duration-and-benefits/ | Post | Blog | MIGRATE | — | Real post
6 | /best-online-aviation-courses-in-india-flexible-learning-for-future-flyers/ | Post | Blog | MIGRATE | — | Real post
7 | /about/ | Page | Brand | MIGRATE | — | Canonical About (founder story: Sumaiya Ali)
8 | /about-us/ | Page | Brand | MIGRATE | — | Duplicate About — pick ONE canonical with /about
9 | /windchasers-meet-the-team/ | Page | Brand | MIGRATE | /team | App has /team; rebuild at live slug
10 | /with-the-founder/ | Page | Brand | MIGRATE | — | Low priority; could fold into About
11 | /contact-us/ | Page | Brand | MIGRATE | — | Phone/email/address verified
12 | /pilot-training-in-india/ | Page | Geo | MIGRATE | /international | App /international covers all; split per live slug
13 | /pilot-training-in-usa/ | Page | Geo | MIGRATE | /international | Geo SEO page
14 | /pilot-training-in-canada/ | Page | Geo | MIGRATE | /international | Geo SEO page
15 | /pilot-training-in-australia/ | Page | Geo | MIGRATE | /international | Geo SEO page
16 | /pilot-training-in-new-zealand/ | Page | Geo | MIGRATE | /international | Geo SEO page
17 | /pilot-training-in-south-africa/ | Page | Geo | MIGRATE | /international | Geo SEO page
18 | /dgca-ground-classes/ | Page | Ground | MIGRATE | /dgca | App has /dgca; rebuild at live slug
19 | /diploma-in-aviation/ | Page | Ground | MIGRATE | — | Core SEO
20 | /ielts-training-program/ | Page | Ground | MIGRATE | — | Core SEO
21 | /privacy-policy/ | Page | Legal | MIGRATE | — | Legal
22 | /refund-policy/ | Page | Legal | MIGRATE | — | Legal
23 | /terms-conditions/ | Page | Legal | MIGRATE | — | Legal
24 | /commercial-pilot-license/ | Page | License | MIGRATE | — | Core SEO
25 | /private-pilot-license/ | Page | License | MIGRATE | — | Core SEO
26 | /airline-transport-pilot-license/ | Page | License | MIGRATE | — | Core SEO
27 | /foreign-cpl/ | Page | License | MIGRATE | — | Core SEO
28 | /license-conversion-course/ | Page | License | MIGRATE | — | Core SEO
29 | /pre-cadet-program/ | Page | Program | MIGRATE | — | Core SEO
30 | /cadet-pilot-program/ | Page | Program | MIGRATE | — | Core SEO
31 | /airline-preparation-program/ | Page | Program | MIGRATE | — | Core SEO
32 | /airline-cadet-program-interview-training/ | Page | Program | MIGRATE | — | Core SEO
33 | /airline/ | Page | Program | MIGRATE | — | Core SEO
34 | /instrument-rating/ | Page | Rating | MIGRATE | — | Core SEO
35 | /multi-engine-rating/ | Page | Rating | MIGRATE | — | Core SEO
36 | /multi-engine-instrument-rating-meir/ | Page | Rating | MIGRATE | — | Core SEO (also dup post — drop post)
37 | /certified-flight-instructor/ | Page | Rating | MIGRATE | — | Core SEO
38 | /night-rating-progam/ | Page | Rating | MIGRATE | — | Keep live typo "progam" in slug
39 | /helicopter-training/ | Page | Training | MIGRATE | /helicopter | App has /helicopter; rebuild at live slug
40 | /cabin-crew-program/ | Page | Training | MIGRATE | /cabin-crew | App has /cabin-crew; rebuild at live slug
41 | /women-in-aviation/ | Page | Training | MIGRATE | — | Core SEO
42 | /boeing-737-type-rating/ | Page | Type Rating | MIGRATE | — | Core SEO
43 | /airbus-a320-type-rating/ | Page | Type Rating | MIGRATE | — | Core SEO
44 | / | Page | Brand | HAVE | / | Home exists; restyle/merge live content if desired
45 | /airport-operations-webinar/ | Page | Funnel | SKIP | /webinar | App has webinar
46 | /airport-operations-webinar-parents/ | Page | Funnel | SKIP | /webinar/parents | App has it
47 | /open-house/ | Page | Funnel | SKIP | /open-house | App has it
48 | /nz-event-rsvp/ | Page | Funnel | SKIP | /nz-seminar | App has it
49 | /thank-you/ | Page | Funnel | SKIP | /thank-you | App has it
50 | /pilot-assessment-test/ | Page | Funnel | SKIP | /assessment | App has assessment
51 | /pilot-assesment-test/ | Page | Funnel | SKIP | /assessment | Typo dup
52 | /pat2/ | Page | Funnel | SKIP | /assessment | Assessment variant
53 | /pat3/ | Page | Funnel | SKIP | /assessment | Assessment variant
54 | /pat4-0/ | Page | Funnel | SKIP | /assessment | Assessment variant
55 | /pilot-assesment-student-onbaording/ | Page | Funnel | SKIP | /assessment | Onboarding funnel
56 | /join-windchasers/ | Page | Funnel | SKIP | — | Recruitment landing
57 | /join-windchasers-proxe/ | Page | Funnel | SKIP | — | Recruitment landing
58 | /cabin-crew-launch/ | Page | Funnel | SKIP | — | Campaign landing
59 | /pilot-training-consultation/ | Page | Funnel | SKIP | /demo | Consultation funnel
60 | /scholarship-application-form/ | Page | Funnel | SKIP | — | Form
61 | /cpl-enquiry/ | Page | Funnel | SKIP | — | Form
62 | /e-registration/ | Page | Funnel | SKIP | — | Form
63 | /priority-pass/ | Page | Funnel | SKIP | — | Lead magnet
64 | /pilot-roadmap-guide-2025/ | Page | Funnel | SKIP | — | Lead magnet
65 | /dgca-demo-sessions/ | Page | Funnel | SKIP | — | Demo funnel
66 | /cabin-crew-purchase-confirm/ | Page | Transactional | SKIP | — | Confirm page
67 | /cabincrew-thankyou/ | Page | Transactional | SKIP | — | Thank-you
68 | /about-thank-you/ | Page | Transactional | SKIP | — | Thank-you
69 | /pat-thank-you/ | Page | Transactional | SKIP | — | Thank-you
70 | /pilot-assesment-thank-you/ | Page | Transactional | SKIP | — | Thank-you
71 | /pilot-assessment-thank-you-2/ | Page | Transactional | SKIP | — | Thank-you
72 | /checkout/ | Page | WooCommerce | SKIP | — | Woo
73 | /cart/ | Page | WooCommerce | SKIP | — | Woo
74 | /my-account/ | Page | WooCommerce | SKIP | — | Woo
75 | /shop/ | Page | WooCommerce | SKIP | — | Woo
76 | /some/ | Page | Junk | DROP | — | Draft dup of license-conversion
77 | /home2/ | Page | Junk | DROP | — | Duplicate homepage draft
78 | /windchasers-anybody-can-fly-top-pilot-training-academy/ | Page | Junk | DROP | — | Old home draft
79 | /privacy-policy-2/ | Page | Junk | DROP | — | Duplicate of privacy-policy
80 | /aviation-safety-briefing/ | Post | Thin | DROP | — | Thin Sept-2023 lead post
81 | /industry-partnership-announcement/ | Post | Thin | DROP | — | Thin lead post (Open House for women)
82 | /pilot-career-workshop/ | Post | Thin | DROP | — | Thin Sept-2023 lead post
83 | /advanced-flight-training-demo/ | Post | Thin | DROP | — | Thin Sept-2023 lead post
84 | /multi-engine-instrument-rating-meir/ (post) | Post | Thin | DROP | — | Duplicate of the page

## Current App Pages
Route (new app) | On Live Site? | Status | Notes
/ | Yes | HAVE | Home
/dgca | Yes (diff slug) | HAVE | Live: /dgca-ground-classes
/helicopter | Yes (diff slug) | HAVE | Live: /helicopter-training
/cabin-crew | Yes (diff slug) | HAVE | Live: /cabin-crew-program
/international | Yes (split) | HAVE | Live: 6 geo pages
/team | Yes (diff slug) | HAVE | Live: /windchasers-meet-the-team
/open-house | Yes | HAVE | Live: /open-house
/webinar | Yes | HAVE | Live: /airport-operations-webinar
/webinar/parents | Yes | HAVE | Live: ...-webinar-parents
/webinar/students | Partial | HAVE | Webinar variant
/assessment | Yes | HAVE | Live: PAT / pilot-assessment-test
/assessment/early | Partial | HAVE | Assessment variant
/nz-seminar | Yes | HAVE | Live: /nz-event-rsvp
/thank-you | Yes | HAVE | Live: /thank-you
/demo | Yes | HAVE | Live: /pilot-training-consultation
/pilot-training | No | APPONLY | App campaign funnel
/pilot-training-students | No | APPONLY | App campaign funnel
/pilot-training-parents | No | APPONLY | App campaign funnel
/flight-schools | No | APPONLY | App feature (map)
/summercamp | No | APPONLY | App campaign
/atc | No | APPONLY | App campaign
/agent | No | APPONLY | Internal tool
/gtm | No | APPONLY | Internal tool
/stitch | No | APPONLY | Internal tool
/admin | No | APPONLY | Internal tool

## Legend & Summary
WindChasers Migration — Legend & Summary
Color legend
MIGRATE | MIGRATE — core SEO page, must rebuild
HAVE | HAVE — equivalent already in new app
SKIP | SKIP — funnel/event/transactional/Woo (covered or not needed)
DROP | DROP — junk / duplicate / thin
APPONLY | APP-ONLY — exists in new app, not on live (keep as-is)
Counts (live URLs)
Status | Count
MIGRATE | 43
HAVE | 1
SKIP | 31
DROP | 9
TOTAL live URLs | =SUM(B12:B15)